## Summary
ISD 287 North Education Center
Job Name | ISD 287 North Education Center
Job Number | ALL022B
Client | All Systems
Project Manager | Jesse
Engineer | David S.
Sales | Todd J.
Labor Report |  | $ Reporting
Budgeted Lead Hours | 150 | Budgeted Lead Dollars | 7950
Lead Hours Used | 16.25 | Lead Dollars Used | 861.25
Lead Hours Remaining | 133.75 | Lead Dollars Remaining | 7088.75
Budgeted Tech Hours | 84 | Budgeted Inst Dollars | 3276
Tech Hours Used | 7.5 | Tech Dollars Used | 292.5
Tech Hours Remaining | 76.5 | Tech Dollars Remaining | 2983.5
Total Budgeted Time | 234 | Total Budgeted Dollars | 11226
Total Time Used | 23.75 | Total Dollars Used | 1153.75
Total Time Remaining | 210.25 | Total Dollars Remaining | 10072.25
Completed | 35%
Remaining | 65%
Hours Summary | Lead | Tech
2012-07-23 | 7.5 | 7.5
2012-07-24 | 8.75 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## Change Order Log
CHANGE ORDER CONTROL LOG:
Project Name: |  |  | ISD 287 North Education Center |  |  |  |  | Project #: | ALL022B
Project Manager: |  |  | Jesse |  |  |  |  | Report Date: | 2012-08-07
Change Order Number | Change Order PDF | Quote # | Description of Change | Impact | Room ID | Type of Change | Requestor | Date Submitted | Evaluator | Status / Decision | Decision Date | PCR is Customer Billable | Price Impact of PCR (Sell) | Project Budget Before Change (Sell) | Project Budget After Change (Sell) | Price Impact of PCR (Cost) | Project Budget Before Change (Cost) | Project Budget After Change (Cost) | Alpha Video Completion Date | Date Billed | Data Validation (Drop Down Values)
1 | [20 empty] | Type of Change | Status / Decision
2 | [20 empty] | Hardware | Accepted As Submitted
3 | [20 empty] | Scope of Work | Accepted w/ Revisions
4 | [20 empty] | Materials | Escalated
5 | [20 empty] | System Conf/Software | Deferred
6 | [20 empty] | Schedule Change | Rejected
7 | [20 empty] | Process Change
8 | [20 empty] | Consolidation / Shipping
9 | [20 empty] | Other
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on B4: Matt Brand: Paste PDF into this column
Note on F4: Options are: 1: High 2: Medium 3: Low
Note on I4: Who identified the change needed?
Note on K4: Who will decide what action is taken on the change?
Note on L4: Options are: Under Review Accepted Deferred Rejected
Note on Y5: Options are: Under Review Accepted Deferred Rejected

## Punch List
Punchlist
Project Name: | ISD 287 North Education Center |  |  | Project #: | ALL022B | Project Manager: | Jesse
Room/Location | Date Entered | Requestor | Owner | Status | Task/Issue | Description | Notes/Comments | Date Completed | Completed By (Initials) | PDF Document
Open
In Progress
Urgent
Complete

## Issue Tracking
Issue Tracking
Project Name: | ISD 287 North Education Center |  |  | Project Number | ALL022B |  | Project Manager: | Jesse
Room/Location | Date Entered | Requestor | Owner | Status | Due Date | Issue | Cause of Issue | Resolution | Date Completed | Completed By (Initials) | PDF Document
A112/ | 2012-04-16 | RAV | JS | OPEN | ASAP | Horizontal Bracing within walls not allowing cable runs | Construction
A121/ | 2012-04-16 | RAV | JS | OPEN | ASAP | Horizontal Bracing within walls not allowing cable runs | Construction
C117/ | 2012-04-16 | RAV | JS | OPEN | ASAP | Horizontal Bracing within walls not allowing cable runs | Construction
C121/ | 2012-04-16 | RAV | JS | OPEN | ASAP | Horizontal Bracing within walls not allowing cable runs | Construction
C123/ | 2012-04-16 | RAV | JS | OPEN | ASAP | Horizontal Bracing within walls not allowing cable runs | Construction
C126/ | 2012-04-16 | RAV | JS | Closed | ASAP | Plate Location required
Multiple Rooms | 2012-04-16 | Alpha | JS | Closed | ASAP | When is electrician to move hi/low voltage boxes at board locations? | Boxes not in correct location per Chad Maxa. He has talked to TSP regarding the issue. No timeline set yet.
Smart Board Delivery | 2012-04-16 | Alpha | JS | Closed |  | Smart Board and Projector Delivery (OFE) Construction crew has not been made aware of this timeline. Delivery is to be on June 25th per Chad Maxa. | Chad Maxa is providing | Needs to be discussed so all contractors are on the same page with the client (ISD 287) Chad Maxa has stated the boards will be delivered to the NEC on June 25th.

## IP Addresses
Client: | ISD 287 North Education Center | [5 empty] | IP Range: |  | 10.74.7.17- .254 | SEE UNAVAILABLE ADDRESSES BELOW!!
Project: | ALL022B | [5 empty] | Subnet Mask: |  | 255.255.255.0
QuoteWorks #: | [6 empty] | Default Gateway: |  | 10.74.7.1
Engineer: | David S. | [5 empty] | DNS: |  | 10.74.12.64
Sales: | Todd J. | [7 empty] | smtp.district287.org
Project Manager: | Jesse | [5 empty] | IP Addresses NOT AVAILABLE!! |  | 10.74.7.10-16 & 10.74.7.231-233
IP Address List
Location Rm-Const/New | Device | Serial Number | IP Address | Subnet Mask | Default Gateway | MAC Address | DNS 1 | DNS 2 | Multicast | System Name | Notes
A112/ A149 | Vbrick Decoder | AW0111250674 |  | 255.255.255.0 | 10.74.7.1 | E0-53-91-3D-84-36 | 10.74.12.64 |  |  | Room A149
A112/ A149 | ILS Controller |  | 10.74.7.70 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A149
A114/ A141 | Vbrick Decoder | AW0111250912 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-24 | 10.74.12.64 |  |  | Room A141
A114/ A141 | ILS Controller |  | 10.74.7.71 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A141
A115/ A139 | Vbrick Decoder | AW0111250738 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-76 | 10.74.12.64 |  |  | Room A139
A115/ A139 | ILS Controller |  | 10.74.7.72 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A139
A117/ A131 | Vbrick Decoder | AW0111250113 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-05 | 10.74.12.64 |  |  | Room A131
A117/ A131 | ILS Controller |  | 10.74.7.73 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A131
A130/ A132 | Vbrick Decoder | AW0111250579 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-D7 | 10.74.12.64 |  |  | Room A132
A130/ A132 | ILS Controller |  | 10.74.7.74 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A132
A118/ A127 | Vbrick Decoder | AW0111250362 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-FE | 10.74.12.64 |  |  | Room A127
A118/ A127 | ILS Controller |  | 10.74.7.75 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A127
A120/ A121 | Vbrick Decoder | AW0111250509 |  | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-91 | 10.74.12.64 |  |  | Room A121
A120/ A121 | ILS Controller |  | 10.74.7.76 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A121
A121/ A109 | Vbrick Decoder | AW0111250852 | 10.74.7.17 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-E8 | 10.74.12.64 |  |  | Room A109
A121/ A109 | ILS Controller |  | 10.74.7.77 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A109
A123/ A101 | Vbrick Decoder | AW0111250582 | 10.74.7.18 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-DA | 10.74.12.64 |  |  | Room A101
A123/ A101 | ILS Controller |  | 10.74.7.78 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A101
A128/ A128 | Vbrick Decoder | AW0111250356 | 10.74.7.19 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-F8 | 10.74.12.64 |  |  | Room A128
A128/ A128 | ILS Controller |  | 10.74.7.79 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A128
B142/ B166 | Vbrick Decoder | AW0111250578 | 10.74.7.20 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-D6 | 10.74.12.64 |  |  | Room B166 | NO SYSTEM REQUIRED IN THIS ROOM PER CLIENT
B142/ B166 | ILS Controller |  | 10.74.7.80 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B166
B145/ B152 | Vbrick Decoder | AW0111250691 | 10.74.7.21 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-47 | 10.74.12.64 |  |  | Room B152 | NO SYSTEM REQUIRED IN THIS ROOM PER CLIENT
B145/ B152 | ILS Controller |  | 10.74.7.81 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B152
B140/ B147 | Vbrick Decoder | AW0111250576 | 10.74.7.22 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-D4 | 10.74.12.64 |  |  | Room B147
B140/ B147 | ILS Controller |  | 10.74.7.82 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B147
B146B/ B148C | Vbrick Decoder | AW0111250551 | 10.74.7.23 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-BB | 10.74.12.64 |  |  | Room B148C | NO SYSTEM REQUIRED IN THIS ROOM PER CLIENT
B146B/ B148C | ILS Controller |  | 10.74.7.83 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B148C
B150B/ B142C | Vbrick Decoder | AW0111250128 | 10.74.7.24 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-14 | 10.74.12.64 |  |  | Room B142C | NO SYSTEM REQUIRED IN THIS ROOM PER CLIENT
B150B/ B142C | ILS Controller |  | 10.74.7.84 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B142C
C116/ C102 | Vbrick Decoder | AW0111250660 | 10.74.7.25 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-28 | 10.74.12.64 |  |  | Room C102
C116/ C102 | ILS Controller |  | 10.74.7.85 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C102
C117/ C106 | Vbrick Decoder | AW0111250316 | 10.74.7.26 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-D0 | 10.74.12.64 |  |  | Room C106
C117/ C106 | ILS Controller |  | 10.74.7.86 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C106
C118/ C110 | Vbrick Decoder | AW0111250413 | 10.74.7.27 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-31 | 10.74.12.64 |  |  | Room C110
C118/ C110 | ILS Controller |  | 10.74.7.87 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C110
C119/ C114 | Vbrick Decoder | AW0111251002 | 10.74.7.28 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-F7-CA | 10.74.12.64 |  |  | Room C114
C119/ C114 | ILS Controller |  | 10.74.7.88 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C114
C120/ C120 | Vbrick Decoder | AW0111250672 | 10.74.7.29 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-34 | 10.74.12.64 |  |  | Room C120
C120/ C120 | ILS Controller |  | 10.74.7.89 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C120
C121/ C124 | Vbrick Decoder | AW0111250844 | 10.74.7.30 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-E0 | 10.74.12.64 |  |  | Room C124
C121/ C124 | ILS Controller |  | 10.74.7.90 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C124
C122/ C132 | Vbrick Decoder | AW0111250822 | 10.74.7.31 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-CA | 10.74.12.64 |  |  | Room C132
C122/ C132 | ILS Controller |  | 10.74.7.91 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C132
C123/ C136 | Vbrick Decoder | AW0111250842 | 10.74.7.32 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-DE | 10.74.12.64 |  |  | Room C136
C123/ C136 | ILS Controller |  | 10.74.7.92 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C136
A214/ A231 | Vbrick Decoder | AW0111250713 | 10.74.7.33 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-5D | 10.74.12.64 |  |  | Room A231
A214/ A231 | ILS Controller |  | 10.74.7.93 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A231
A216/ A227 | Vbrick Decoder | AW0111250846 | 10.74.7.34 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-E2 | 10.74.12.64 |  |  | Room A227
A216/ A227 | ILS Controller |  | 10.74.7.94 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A227
A219/ A221 | Vbrick Decoder | AW0111250807 | 10.74.7.35 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-BB | 10.74.12.64 |  |  | Room A221
A219/ A221 | ILS Controller |  | 10.74.7.95 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A221
A221/ A217 | Vbrick Decoder | AW0111250184 | 10.74.7.36 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-4C | 10.74.12.64 |  |  | Room A217
A221/ A217 | ILS Controller |  | 10.74.7.96 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A217
A224/ A211 | Vbrick Decoder | AW0111250482 | 10.74.7.37 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-76 | 10.74.12.64 |  |  | Room A211
A224/ A211 | ILS Controller |  | 10.74.7.97 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A211
A211/ A235 | Vbrick Decoder | AW0111250777 | 10.74.7.38 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-9D | 10.74.12.64 |  |  | Room A235
A211/ A235 | ILS Controller |  | 10.74.7.98 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A235
A210/ A238 | Vbrick Decoder | AW0111251331 | 10.74.7.39 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-F9-13 | 10.74.12.64 |  |  | Room A238
A210/ A238 | ILS Controller |  | 10.74.7.99 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A238
A230/ A206 | Vbrick Decoder | AW0111250818 | 10.74.7.40 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-C6 | 10.74.12.64 |  |  | Room A206
A230/ A206 | ILS Controller |  | 10.74.7.100 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A206
A229/ A201 | Vbrick Decoder | AW0111250384 | 10.74.7.41 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-14 | 10.74.12.64 |  |  | Room A201
A229/ A201 | ILS Controller |  | 10.74.7.101 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A201
A226/ A205 | Vbrick Decoder | AW0111250324 | 10.74.7.42 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-D8 | 10.74.12.64 |  |  | Room A205
A226/ A205 | ILS Controller |  | 10.74.7.102 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room A205
B216/ B220 | Vbrick Decoder | AW0111250464 | 10.74.7.43 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-64 | 10.74.12.64 |  |  | Room B220
B216/ B220 | ILS Controller |  | 10.74.7.103 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B220
B218/ B222 | Vbrick Decoder | AW0111250121 | 10.74.7.44 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-0D | 10.74.12.64 |  |  | Room B222
B218/ B222 | ILS Controller |  | 10.74.7.104 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B222
B229/ B243 | Vbrick Decoder | AW0111250904 | 10.74.7.45 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-1C | 10.74.12.64 |  |  | Room B243
B229/ B243 | ILS Controller |  | 10.74.7.105 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B243
B227/ B244 | Vbrick Decoder | AW0111250914 | 10.74.7.46 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-26 | 10.74.12.64 |  |  | Room B244
B227/ B244 | ILS Controller |  | 10.74.7.106 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B244
B225/ B240 | Vbrick Decoder | AW0111250931 | 10.74.7.47 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-37 | 10.74.12.64 |  |  | Room B240
B225/ B240 | ILS Controller |  | 10.74.7.107 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B240
B224/ B234 | Vbrick Decoder | AW0111250444 | 10.74.7.48 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-50 | 10.74.12.64 |  |  | Room B234
B224/ B234 | ILS Controller |  | 10.74.7.108 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B234
B221/ B230 | Vbrick Decoder | AW0111250350 | 10.74.7.49 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-F2 | 10.74.12.64 |  |  | Room B230
B221/ B230 | ILS Controller |  | 10.74.7.109 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B230
C216/ C202 | Vbrick Decoder | AW0111250109 | 10.74.7.50 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-82-01 | 10.74.12.64 |  |  | Room C202
C216/ C202 | ILS Controller |  | 10.74.7.110 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C202
C218/ C210 | Vbrick Decoder | AW0111250811 | 10.74.7.51 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-BF | 10.74.12.64 |  |  | Room C210
C218/ C210 | ILS Controller |  | 10.74.7.111 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C210
C220/ C212 | Vbrick Decoder | AW0111250736 | 10.74.7.52 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-74 | 10.74.12.64 |  |  | Room C212
C220/ C212 | ILS Controller |  | 10.74.7.112 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C212
C222/ C216 | Vbrick Decoder | AW0111250961 | 10.74.7.53 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-55 | 10.74.12.64 |  |  | Room C216
C222/ C216 | ILS Controller |  | 10.74.7.113 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C216
C224/ C218 | Vbrick Decoder | AW0111250816 | 10.74.7.54 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-C4 | 10.74.12.64 |  |  | Room C218
C224/ C218 | ILS Controller |  | 10.74.7.114 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C218
C225/ C220 | Vbrick Decoder | AW0111250851 | 10.74.7.55 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-E7 | 10.74.12.64 |  |  | Room C220
C225/ C220 | ILS Controller |  | 10.74.7.115 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C220
C227/ C226 | Vbrick Decoder | AW0111250805 | 10.74.7.56 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-B9 | 10.74.12.64 |  |  | Room C226
C227/ C226 | ILS Controller |  | 10.74.7.116 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room C226
B301/ B315 | Vbrick Decoder | AW0111250705 | 10.74.7.57 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-55 | 10.74.12.64 |  |  | Room B315
B301/ B315 | ILS Controller |  | 10.74.7.117 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B315
B303/ B311 | Vbrick Decoder | AW0111250395 | 10.74.7.58 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-1F | 10.74.12.64 |  |  | Room B311
B303/ B311 | ILS Controller |  | 10.74.7.118 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B311
B311/ B305 | Vbrick Decoder | AW0111250443 | 10.74.7.59 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-4F | 10.74.12.64 |  |  | Room B305
B311/ B305 | ILS Controller |  | 10.74.7.119 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B305
B313/ B301 | Vbrick Decoder | AW0111250560 | 10.74.7.60 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-C4 | 10.74.12.64 |  |  | Room B301
B313/ B301 | ILS Controller |  | 10.74.7.120 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B301
B306/ B310 | Vbrick Decoder | AW0111250473 | 10.74.7.61 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-6D | 10.74.12.64 |  |  | Room B310
B306/ B310 | ILS Controller |  | 10.74.7.121 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B310
B304/ B314 | Vbrick Decoder | AW0111250812 | 10.74.7.62 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-84-C0 | 10.74.12.64 |  |  | Room B314
B304/ B314 | ILS Controller |  | 10.74.7.122 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B314
B326/ B321 | Vbrick Decoder | AW0111250537 | 10.74.7.63 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-83-AD | 10.74.12.64 |  |  | Room B321
B326/ B321 | ILS Controller |  | 10.74.7.123 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B321
B328/ B325 | Vbrick Decoder | AW0111250924 | 10.74.7.64 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D-85-30 | 10.74.12.64 |  |  | Room B325
B328/ B325 | ILS Controller |  | 10.74.7.124 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B325
B330/ B334 | Vbrick Decoder |  | 10.74.7.65 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D | 10.74.12.64 |  |  | Room B334
B330/ B334 | ILS Controller |  | 10.74.7.125 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B334
B332/ B338 | Vbrick Decoder |  | 10.74.7.66 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D | 10.74.12.64 |  |  | Room B338
B332/ B338 | ILS Controller |  | 10.74.7.126 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B338
B333/ B335 | Vbrick Decoder |  | 10.74.7.67 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D | 10.74.12.64 |  |  | Room B335
B333/ B335 | ILS Controller |  | 10.74.7.127 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B335
B336/ B331 | Vbrick Decoder |  | 10.74.7.68 | 255.255.255.0 | 10.74.7.1 | E0-91-53-3D | 10.74.12.64 |  |  | Room B331
B336/ B331 | ILS Controller |  | 10.74.7.128 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64 |  |  | Room B331
| Vbrick Encoder Blade |  | 10.74.7.150 - 239.22.118.150 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.151 - 239.22.118.151 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.152 - 239.22.118.152 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.153 - 239.22.118.153 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.154 - 239.22.118.154 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.155 - 239.22.118.155 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.156 - 239.22.118.156 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.157 - 239.22.118.157 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.158 - 239.22.118.158 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.159 - 239.22.118.159 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Blade |  | 10.74.7.160 - 239.22.118.160 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick Encoder Stand-Alone |  | 10.74.7.161 - 239.22.118.161 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
|  |  |  | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick VEMS Server |  | 10.74.7.200 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
| Vbrick VOD-W Server |  | 10.74.7.201 | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64
|  |  |  | 255.255.255.0 | 10.74.7.1 |  | 10.74.12.64

## Crestron Config.
Crestron Configuration Form
Room/Location | Device / Purpose | IP Address / Notes

## Daily Report
[11 empty] | Job Name | ISD 287 North Education Center | [101 empty] | Position Validation |  | Job Status Validation
[8 empty] | 7711 Computer Avenue |  |  | Job Number | ALL022B | [103 empty] | On Schedule
[8 empty] | Edina, MN 55435 |  |  | Client | All Systems | [101 empty] | Lead |  | Behind Schedule
[11 empty] | Project Manager | Jesse | [101 empty] | Eng |  | Ahead of Schedule
Version 1.5 | [10 empty] | Engineer | David S. | [101 empty] | PM |  | Complete
Updated 3/13/12 | [10 empty] | Sales | Todd J. | [101 empty] | Tech
Daily Job Report
General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information |  |  | General Information
Date |  | 2012-07-23 | Date |  | 2012-07-24 | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date
Lead Tech |  | Zac Drechsler | Lead Tech |  | Zac Drechsler | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech |  |  | Lead Tech
Job Progress |  | 30% | Job Progress |  | 35% | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress |  |  | Job Progress
Job is |  | Behind Schedule | Job is |  | Behind Schedule | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is |  |  | Job is
Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees |  |  | Employees
Name |  | Zac Drechsler | Name |  | Zac Drechsler | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name
Title |  | Lead | Title |  | Lead | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title
Hours Worked |  | 6.5 | Hours Worked |  | 7.75 | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked
Travel |  | 1 | Travel |  | 1 | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel
Work Performed |  | Rack gear, dress lines, find gear, etc | Work Performed |  | terminated sound masking and paging lines. | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed
Name |  | Greg Kennard | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name
Title |  | Tech | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title
Hours Worked |  | 6.5 | Hours Worked |  | 2.5 | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked
Travel |  | 1 | Travel |  | 1 | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel
Work Performed |  | Rack gear, dress power, etc | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed
Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name
Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title
Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked
Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel
Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed
Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name |  |  | Name
Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title |  |  | Title
Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked |  |  | Hours Worked
Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel |  |  | Travel
Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed |  |  | Work Performed
Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description | Materials Received On Site | QTY | Description
QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description
On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.) |  |  | On Site Equipment (Lifts/Scaffold/Tools/etc.)
QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description | QTY |  | Description
Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues |  |  | Comments/Concerns/Issues
Are we ordering a Mid Atlantic VSR and if so does it hold all 3 PC's?? Also are we ordering a rack mount for the 19" dell monitor? |  |  | Need drawings for Gym system ASAP.
Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work | Change Orders/Additional Work |  | Change Orders/Additional Work
Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time |  |  | Total Time
2012-07-23 | Lead | 7.5 | 2012-07-24 | Lead | 8.75 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0
2012-07-23 | Lead | 0 | 2012-07-24 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0
2012-07-23 | Lead | 0 | 2012-07-24 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0
2012-07-23 | Lead | 0 | 2012-07-24 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0 | 0 | Lead | 0
2012-07-23 | Tech | 0 | 2012-07-24 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0
2012-07-23 | Tech | 7.5 | 2012-07-24 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0
2012-07-23 | Tech | 0 | 2012-07-24 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0
2012-07-23 | Tech | 0 | 2012-07-24 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0 | 0 | Tech | 0

## Project Contacts
Alpha Video Contacts
Name | Title | Desk Phone | Cell Phone | Notes |  |  | Jamin Johnson | Manager Integration | 952.841.3393 | 612.309.9542
Todd Johnson | Education Sales | 952.841.3331 | 612.817.5238 |  |  |  | Jesse Stunes | Project Manager | 952.841.3337 | 612.282.8641
David Soukup | #N/A | #N/A | #N/A |  |  |  | Jake Remus | Project Manager | 952.841.3334 | 612.387.1494
Jesse Stunes | Project Manager | 952.841.3337 | 612.282.8641 |  |  |  | Matt Brand | Project Manager | 952.841.3368 | 612.205.1071
| #N/A | #N/A | #N/A |  |  |  | Doug Melaas | Engineer | 952.841.3362 | 612.616.8056
| #N/A | #N/A | #N/A |  |  |  | David Soukop | Engineer | 952.841.3353 | 651.434.1880
| #N/A | #N/A | #N/A |  |  |  | Brian Mathison | Integration Specialist - ENG | 952.841.3346 | 651.503.6143
| #N/A | #N/A | #N/A |  |  |  | Kurt Lundblad | Engineer | 952.841.3354 | 415.309.9563
| #N/A | #N/A | #N/A |  |  |  | David Muth | Engineer | 952.841.3321 | 612.868.6963
| #N/A | #N/A | #N/A |  |  |  | Jeff Volk | Systems Sales Executive | 952.841.3311 | 612.719.6234
| #N/A | #N/A | #N/A |  |  |  | Todd Johnson | Education Sales | 952.841.3331 | 612.817.5238
| #N/A | #N/A | #N/A |  |  |  | Bryan Nelson | Systems Sales Executive | 952.841.3304 | 612.819.7213
| #N/A | #N/A | #N/A |  |  |  | Bob Follestad | Systems Sales Executive | 952.841.3302 | 612.240.7257
| #N/A | #N/A | #N/A |  |  |  | Mike Pough | Systems Sales Executive | 952.841.3365 | 612.202.3177
| #N/A | #N/A | #N/A |  |  |  | Chad Jensen | Systems Sales Executive | 952.841.3309 | 612.242.2414
External Project Contacts | [6 empty] | Darren Whitten | Systems Sales Executive | 952.841.3332 | 612.281.9804
Name | Title | Desk Phone | Cell Phone | Roles | Affiliation | Email Address | Scott Johnson | Systems Sales Executive | 952.841.3361 | 763.647.0587
Jeff Evans | PM | 507.281.9466 | 507.951.3005 | Our Contract Supervisor | All Systems | jevans@allsysinst.com | Brian Beckwith | Lead Broadcast Tech | 952.841.3376 | 612.616.3624
Chad Maxa | Technology | 763.550.7146 | 952.288.9450 | District Tech | ISD 287 | cmaxa@district287.org | Jeff Merrill | Lead | N/A | 630.661.3126
Marty Gibson | Lead Foreman |  | 612.360.0511 | Contract Super/Cabling/Speakers | All Systems |  | Dan Olk | Lead | 952.841.3322 | 320.420.8424
Jeff Walker | Superintendent | 952.830.9000 | 612.290.6957 | Super | JE Dunn | jeff.walker@jedunn.com | Chris Weiss | Lead | 952.841.3380 | 651.428.4540
Don Owens | Sales | 763.544.4400x12 |  | Subcontractor | RAV | dowens@ravtechnologies.com | Matt Rasmusssen | Video Systems Engineer | 952.841.3361 | 612.805.6214
Dan Ekblad | PM |  | 612.750.5451 | Subcontractor | RAV | dekblad@ravetechnologies.com | Kate Bion | Sales Support | 952.841.3301 | 218.310.3850
Tyler Hanna | Electrical Designer | 952.474.3291 |  | Consultant | TSP |  | Jessica Rhodes | Sales Support | 952.841.3308 | 651.503.4513
Jonas Sjoberg | Network Engineer | 763.550.7140 |  | District I.T. | ISD 287 | jsjoberg@district287.org
Mickhail McAnuff | Commissioning Engineer |  | 551.206.1442 | Lighting commissioning | Encelium | mmcanuff@encelium.com
Justin Chapman | Electrical Install |  | 612.703.9011 | Electrical Installation | Elliott Contracting | jachapman@elliottcontracting.com
Jeff Boumeester | Lighting |  |  |  | TSR Lighting | jboumeester@tsrlighting.com
Tom Shultz | Director of Facilities | 763.550.7120 |  |  | ISD 287 | twshultz@district287.org
Paul Balitewicz | Vbrick Sales?/Support |  | 630.229.7310 | Vbrick Support | V Brick

## Serial Numbers
ASP-MG24 | 651400251100030
CP400 | 4711BX01117
CP400 | 4711BX01077
PRS-4P125-US | 2180039508
PRS-4P125-US | 2180039508
NCO-B-US
VOD-W125